## Qtr 2
ACTIVITY ITEM NUMBER | WORK PLAN SIZE | BRIEF DESCRIPTION OF ACTIVITY | DUE DATE
ITEM # 1 | ALL | Attend HCC Meetings | Quarterly
ITEM # 6 | ALL | KS-HAN Drill | Waived
ITEM # 13 | ALL | Maintain/update website and/or social media sites. | 2020-12-31
Revised 12/16/2020

## Qtr 3
ACTIVITY ITEM NUMBER | WORK PLAN SIZE | BRIEF DESCRIPTION OF ACTIVITY | DUE DATE
ITEM # 1 | ALL | Attend HCC Meetings | Quarterly
ITEM # 6 | ALL | KS-HAN Drill | Waived
ITEM # 22 | LARGE | Complete Mental health or psychological first aid training. | 2021-03-31

## Qtr 4
ACTIVITY ITEM NUMBER | WORK PLAN SIZE | BRIEF DESCRIPTION OF ACTIVITY | DUE DATE ON ORIGINAL WORK PLAN | CHANGES NOTED AS OF 12/14/2020 | UPDATES NOTED AS OF 03/10/2021
ITEM # 1 | ALL | Attend HCC Meetings | Quarterly | Quarterly | Quarterly
ITEM # 2 | ALL | Attend a ESF-8 or LEPC planning meeting | 2021-06-30 | 2021-06-30 | 2021-06-30
ITEM # 3 | ALL | Attend Regional PHEP Meetings, Conferences, trainings and/or exercises… | 2021-06-30 | 2021-06-30 | 2021-06-30
ITEM # 6 | ALL | KS-HAN Drill | Quarterly | Quarterly | Waived
ITEM # 8 | ALL | Purchase PHEP supplies/equip | 2021-06-30 | 2021-06-30 | 2021-06-30
ITEM # 9 | SMALL | Use of social media to build community prep and/or for National Preparedness Month. | Optional | Optional | Optional
ITEM # 9 | MEDIUM and LARGE | Use of social media to build community prep and/or for National Preparedness Month. | 2021-06-30 | 2021-06-30 | Waived. We believe most counties met this requirement. Report if you did participate, so that KDHE has numbers to report to CDC.
ITEM # 11A | SMALL | LHD will review and update county plans based on COVID response | 2021-04-30 | 2021-04-30 | Postponed: Not due until next budget period. Postpone until 06/30/2022.
ITEM # 11B | MEDIUM and LARGE | Participate in an annual exercise or real event at the local-level | 2021-04-30 | 2021-04-30 | Partially Postponed: Exercise or real event remains in this budget period. However, AAR/IP is now due 9/30/2021. Suggest LHDs focus on PODs for this AAR/IP.
ITEM # 14 | ALL | Obtain or renew certification for Packaging and Shipping and KHEL: Preparing Clinical Specimens Related to Chemical or Biological. | 2021-06-30 | 2021-06-30 | 2021-06-30
ITEM # 15 | ALL | Annual fit testing | 2021-06-30 | 2021-06-30 | 2021-06-30
ITEM # 15 | ALL | Submit Mass Dispensing SOG. | 2020-12-31 | 2021-06-30 | Reduced: Submit the plans to KDHE by June 30,2021, so that KDHE has the plans on file. LHD do not need to review or update, but do need to send in the plans.
ITEM # 15 | ALL | Submit COOP SOG | 2020-12-31 | 2021-06-30 | Reduced: Submit the plans to KDHE by June 30th, so that KDHE has the plans on file. LHD do not need to review or update, but do need to send in the plans.
ITEM # 15 | ALL | Update POD locations and enter into IMATS | 2020-12-31 | 2021-06-30 | Reduced: Waiving entering the POD locations. However, LHDs must log in by 6/30/2021 and indicate on the workplan they have done so. This will keep their IMATS accounts active.
ITEM # 15 | MEDIUM and LARGE | LHD will review and update county plans based on COVID response | 2020-12-31 | 2021-06-30 | Postponed: Not due until next budget period. Postpone until 06/30/2022.
ITEM # 17 | ALL | Attend 3 Preparedness training webinars | Quarterly | 2021-06-30 | 2021-06-30
ITEM # 18 | ALL | Enter PHEP inventory into CRMCS | 2021-05-31 | 2021-05-31 | 2021-05-31
ITEM # 19 | MEDIUM and LARGE | Surge strategy response with staffing matrix | 2021-06-30 | 2021-06-30 | Postponed: Not due until next budget period. Postpone until 09/30/2021.
ITEM # 20 | LARGE | Comms Training FEMA G0290 | 2021-06-30 | 2021-06-30 | Waived
ITEM # 21 | LARGE | Complete two trainings to address gaps | 2021-06-30 | Complete one training to address gaps by 6/30/2021 | Complete one training to address gaps by 6/30/2021

## All Work Plan Activities
ACTIVITY ITEM NUMBER | WORK PLAN SIZE | BRIEF DESCRIPTION OF ACTIVITY | DUE DATE ON ORIGINAL WORK PLAN | DUE DATE NOTED AS OF 12/14/2020 | UPDATES NOTED AS OF 03/10/2021
ITEM # 1 | ALL | Attend HCC Meetings | Quarterly | Quarterly | Quarterly
ITEM # 2 | ALL | LHD will participate in a ESF-8 or LEPC planning meeting | 2021-06-30 | 2021-06-30 | 2021-06-30
ITEM # 3 | ALL | Attend Regional PHEP Meetings, Conferences, trainings and/or exercises… | 2021-06-30 | 2021-06-30 | 2021-06-30
ITEM # 4 | ALL | NIMS Online Trainings | 2020-09-30 | 2020-10-15 | 2020-10-15
ITEM # 5 | ALL | KS-HAN updated | 2020-09-30 | 2020-10-15 | 2020-10-15
ITEM # 6 | ALL | KS-HAN Drill | Quarterly | Waived | Waived
ITEM # 7 | ALL | IMATS updated | 2020-09-30 | 2020-10-15 | 2020-10-15
ITEM # 8 | ALL | Purchase PHEP supplies/equip | 2021-06-30 | 2021-06-30 | 2021-06-30
ITEM # 9 | SMALL | Use of social media to build community prep and/or for National Preparedness Month. | Optional | Optional | Optional
ITEM # 9 | MEDIUM and LARGE | Use of social media to build community prep and/or for National Preparedness Month. | 2021-06-30 | 2021-06-30 | Waived. We believe most counties met this requirement. Report if you did participate, so that KDHE has numbers to report to CDC.
ITEM # 10 | ALL | EPI Hotline updated | 2020-09-30 | 2020-10-15 | 2020-10-15
ITEM # 11 | ALL | AAR/IP from COVID-19 BP1 response | 2020-09-30 | 2020-10-15 | 2020-10-15
ITEM # 11A | SMALL | LHD will review and update county plans based on COVID response | 2021-04-30 | 2021-04-30 | Postponed: Not due until next budget period. Postpone until 06/30/2022.
ITEM # 11B | MEDIUM and LARGE | Participate in an annual exercise or real event at the local-level | 2021-04-30 | 2021-04-30 | Partially Postponed: Exercise or real event remains in this budget period. However, AAR/IP is now due 9/30/2021. Suggest LHDs focus on PODs for this AAR/IP.
ITEM # 12 | ALL | LHD will ensure that priority communication services are available in an emergency. | 2020-09-30 | 2020-10-15 | 2020-10-15
ITEM # 13 | ALL | Maintain/update website and/or social media sites. | 2020-12-31 | 2020-12-31 | 2020-12-31
ITEM # 14 | ALL | Obtain or renew certification for Packaging and Shipping and KHEL: Preparing Clinical Specimens Related to Chemical or Biological. | 2021-06-30 | 2021-06-30 | 2021-06-30
ITEM # 15 | ALL | Annual fit testing | 2021-06-30 | 2021-06-30 | 2021-06-30
ITEM # 15 | ALL | Submit Mass Dispensing SOG. | 2020-12-31 | 2021-06-30 | Reduced: Submit the plans to KDHE by June 30, 2021, so that KDHE has the plans on file. LHD do not need to review or update, but do need to send in the plans.
ITEM # 15 | ALL | Submit COOP SOG | 2020-12-31 | 2021-06-30 | Reduced: Submit the plans to KDHE by June 30, 2021, so that KDHE has the plans on file. LHD do not need to review or update, but do need to send in the plans.
ITEM # 15 | ALL | Update POD locations and enter into IMATS | 2020-12-31 | 2021-06-30 | Reduced: Waiving entering the POD locations. However, LHDs must log in by 6/30/2021 and indicate on the workplan they have done so. This will keep their IMATS accounts active.
ITEM # 15 | MEDIUM and LARGE | LHD will review and update county plans based on COVID response | 2020-12-31 | 2021-06-30 | Postponed: Not due until next budget period. Postpone until 06/30/2022.
ITEM # 16 | ALL | New LHD administrators training | 2021-06-30 | Waived | Waived
ITEM # 17 | ALL | Attend 3 Preparedness training webinars | Quarterly | 2021-06-30 | 2021-06-30
ITEM # 18 | ALL | Enter PHEP inventory into CRMCS | 2021-05-31 | 2021-05-31 | 2021-05-31
ITEM # 19 | SMALL | N/A | N/A | N/A | N/A
ITEM # 19 | MEDIUM and LARGE | Surge strategy response with staffing matrix | 2021-06-30 | 2021-06-30 | Postponed: Not due until next budget period. Postpone until 09/30/2021.
ITEM # 20 | SMALL | N/A | N/A | N/A | N/A
ITEM # 20 | MEDIUM | Complete at least one additional in-state training | 2021-03-31 | Waived | Waived
ITEM # 20 | LARGE | Comms Training FEMA G0290 | 2021-06-30 | 2021-06-30 | Waived
ITEM # 21 | SMALL & MEDIUM | N/A | N/A | N/A | N/A
ITEM # 21 | LARGE | Complete two trainings to address gaps | 2021-06-30 | Complete one training to address gaps by 6/30/2021 | Complete one training to address gaps by 6/30/2021
ITEM # 22 | SMALL & MEDIUM | N/A | N/A | N/A | N/A
ITEM # 22 | LARGE | Complete Mental health or psychological first aid training. | 2021-03-31 | 2021-03-31 | 2021-03-31

## Notes
NOTES
For those countys on a Small Work Plan they do not need to remit a Quarter 2 Work Plan. However, they still must remit a Quarter 2 Financial Status Report (FSR) along with uploading any supporting documentation for the FSR to the Uploads Tab in KGMS by 01/15/2021.
Small Work Plan Items - 1, 2, 3, 4, 5, 6, 7, 8, 9 (Optional), 10, 11, 11A, 12, 13, 14, 15A, 15B, 15C, 15D, 17 and18.
Medium Work Plan Items - 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11A, 11B, 12, 13, 14, 15, 15A, 15B, 15C, 15D, 17, 18, and 19.
Large Work Plan Items - 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11A, 11B, 12, 13, 14, 15A, 15B, 15C, 15D, 15E, 17, 18, 19, 20, 21 and 22.
Note: Item # 6 for all work plans was waived by KDHE for Quarter 1 through Quarter 4 due to all the Alert Response notificatiions. Enter "Waived" on the work plan for reporting.
"This publication was supported by the Grant or Cooperative Agreement Number, NU90TP922049, funded by the Centers for Disease Control and Prevention. Its contents are solely the responsibility of the authors and do not necessarily represent the official views of the Centers for Disease Control and Prevention or the Department of Health and Human Services."